## Combined
|  |  | ICU REHAB | [8 empty] | ALI | [8 empty] | PLEURAL PROCEDURES | [8 empty] | JUVENILE ARTHRITIS | [8 empty] | STABILISATION
|  |  | SODIUM | [8 empty] | LEARNING DISABILITIES | [8 empty] | RIB FRACTURES | [8 empty] | EMERGENCY SURGERY
 | time axis 2024-09-01 to 2029-03-01
33 | Report production 2nd review | bar: 2024-09-01 to 2024-10-01
34 | Report production 3rd review | bar: 2024-10-01 to 2024-11-01
35 | To HQIP - SRP | bar: 2024-11-01
36 | Develop QI tools | bar: 2025-01-01 to 2025-04-01
37 | PUBLISH | bar: 2025-06-01
38 | Follow-up work and stakeholder meeting 1 year on | bar: 2025-07-01 to 2026-06-01
29 | Reviewer meetings | bar: 2024-09-01 to 2025-01-01
30 | Data cleaning | bar: 2024-10-01
31 | Data analysis | bar: 2024-11-01 to 2025-01-01
32 | Write the report | bar: 2024-11-01 to 2025-02-01
33 | Report production 1st review | bar: 2025-02-01 to 2025-03-01
34 | Report production 2nd review | bar: 2025-03-01 to 2025-04-01
35 | Report production 3rd review | bar: 2025-04-01 to 2025-05-01
36 | To HQIP - SRP | bar: 2025-06-01
37 | Develop QI tools | bar: 2025-07-01 to 2025-08-01
38 | PUBLISH | bar: 2025-10-01
39 | Follow-up work and stakeholder meeting 1 year on | bar: 2025-11-01 to 2026-10-01
29 | Reviewer meetings | bar: 2024-09-01 to 2025-03-01
30 | Data cleaning | bar: 2024-10-01 to 2024-12-01
31 | Data analysis | bar: 2025-01-01 to 2025-03-01
32 | Write the report | bar: 2025-01-01 to 2025-04-01
33 | Report production 1st review | bar: 2025-04-01 to 2025-05-01
34 | Report production 2nd review | bar: 2025-05-01 to 2025-06-01
35 | Report production 3rd review | bar: 2025-06-01 to 2025-07-01
36 | To HQIP - SRP | bar: 2025-08-01
37 | Develop QI tools | bar: 2025-09-01 to 2025-10-01
38 | PUBLISH | bar: 2025-11-01
39 | Follow-up work and stakeholder meeting 1 year on | bar: 2025-12-01 to 2026-11-01
29 | Reviewer meetings | bar: 2024-09-01 to 2025-03-01
30 | Data cleaning
31 | Data analysis | bar: 2025-01-01 to 2025-03-01
32 | Write the report | bar: 2025-01-01 to 2025-04-01
33 | Report production 1st review | bar: 2025-04-01 to 2025-05-01
34 | Report production 2nd review | bar: 2025-05-01 to 2025-06-01
35 | Report production 3rd review | bar: 2025-06-01 to 2025-07-01
36 | To HQIP - SRP | bar: 2025-09-01
37 | Develop QI tools
38 | PUBLISH | bar: 2025-12-01
39 | Follow-up work and stakeholder meeting 1 year on | bar: 2026-01-01 to 2026-12-01
21 | Advertise the study through primary contacts (LRs) and all stakeholders | bar: 2024-09-01
22 | Advertise for reviewers through all contacts and social media | bar: 2024-09-01
23 | Create the database | bar: 2024-09-01
24 | Start patient identification | bar: 2024-10-01
25 | Clinician questionnaires | bar: 2024-11-01 to 2025-06-01
26 | Organisational questionnaires | bar: 2025-01-01 to 2025-06-01
27 | Online patient/clinican surveys/interviews | bar: 2025-01-01 to 2025-06-01
28 | Appoint and train case reviewers | bar: 2024-12-01
29 | Reviewer meetings | bar: 2025-01-01 to 2025-06-01
30 | Data cleaning | bar: 2025-01-01 to 2025-03-01
31 | Data analysis | bar: 2025-04-01 to 2025-06-01
32 | Write the report | bar: 2025-04-01 to 2025-07-01
33 | Report production 1st review | bar: 2025-07-01 to 2025-08-01
34 | Report production 2nd review | bar: 2025-08-01 to 2025-09-01
35 | Report production 3rd review | bar: 2025-09-01 to 2025-10-01
36 | To HQIP - SRP | bar: 2025-11-01
37 | Develop QI tools | bar: 2025-12-01 to 2026-01-01
38 | PUBLISH | bar: 2026-02-01
39 | Follow-up work and stakeholder meeting 1 year on | bar: 2026-03-01 to 2027-02-01
1 | Meet with the study proposer | bar: 2024-09-01
2 | Form the study advisory group | bar: 2024-10-01 to 2025-01-01
3 | Any similar work programmes/national datasets | bar: 2024-12-01 to 2025-01-01
4 | Literature search | bar: 2024-12-01 to 2025-01-01
5 | First study advisory group meeting - key questions inc. parity of esteem and health inequalities | bar: 2025-01-01
6 | Identify methods of data collection - inclusion and exclusion | bar: 2025-01-01
7 | Set up a study web page and email | bar: 2025-02-01 to 2025-03-01
8 | Develop a communications plan - who should be involved and wider stakeholders | bar: 2025-02-01 to 2025-03-01
9 | Develop a healthcare quality improvement plan | bar: 2025-02-01 to 2025-03-01
10 | Develop a public/patient/carer involvement plan | bar: 2025-02-01 to 2025-03-01
11 | Draft the protocol | bar: 2025-02-01 to 2025-03-01
12 | Draft the questionnaires | bar: 2025-03-01 to 2025-05-01
13 | Second study advisory group meeting | bar: 2025-04-01
14 | Draft the analysis plan | bar: 2025-04-01 to 2025-06-01
15 | Finalise the protocol | bar: 2025-04-01 to 2025-05-01
16 | Finalise the questionnaires | bar: 2025-04-01 to 2025-05-01
17 | Submit CAG approval | bar: 2025-05-01
18 | Update the website | bar: 2025-06-01
19 | Send the protocol and questionnaires to HQIP | bar: 2025-06-01
20 | Send starter packs to local reporters (LRs) | bar: 2025-06-01
21 | Advertise the study through primary contacts (LRs) and all stakeholders | bar: 2025-06-01
22 | Advertise for reviewers through all contacts and social media | bar: 2025-06-01
23 | Create the database | bar: 2025-05-01 to 2025-07-01
24 | Start patient identification | bar: 2025-08-01
25 | Clinician questionnaires | bar: 2025-08-01 to 2026-04-01
26 | Organisational questionnaires | bar: 2025-10-01 to 2026-04-01
27 | Online patient/clinican surveys/interviews | bar: 2025-10-01 to 2026-04-01
28 | Appoint and train case reviewers | bar: 2025-09-01
29 | Reviewer meetings | bar: 2025-09-01 to 2026-03-01
30 | Data cleaning | bar: 2025-10-01 to 2025-12-01
31 | Data analysis | bar: 2026-01-01 to 2026-03-01
32 | Write the report | bar: 2026-01-01 to 2026-04-01
33 | Report production 1st review | bar: 2026-04-01 to 2026-05-01
34 | Report production 2nd review | bar: 2026-05-01 to 2026-06-01
35 | Report production 3rd review | bar: 2026-06-01 to 2026-07-01
36 | To HQIP - SRP | bar: 2026-08-01
37 | Develop QI tools | bar: 2026-09-01 to 2026-10-01
38 | PUBLISH | bar: 2026-11-01
39 | Follow-up work and stakeholder meeting 1 year on | bar: 2026-12-01 to 2027-11-01
1 | Meet with the study proposer | bar: 2024-09-01
2 | Form the study advisory group | bar: 2024-10-01 to 2025-01-01
3 | Any similar work programmes/national datasets | bar: 2024-12-01 to 2025-01-01
4 | Literature search | bar: 2024-12-01 to 2025-01-01
5 | First study advisory group meeting - key questions inc. parity of esteem and health inequalities | bar: 2025-01-01
6 | Identify methods of data collection - inclusion and exclusion | bar: 2025-01-01
7 | Set up a study web page and email | bar: 2025-02-01 to 2025-03-01
8 | Develop a communications plan - who should be involved and wider stakeholders | bar: 2025-02-01 to 2025-03-01
9 | Develop a healthcare quality improvement plan | bar: 2025-02-01 to 2025-03-01
10 | Develop a public/patient/carer involvement plan | bar: 2025-02-01 to 2025-03-01
11 | Draft the protocol | bar: 2025-02-01 to 2025-03-01
12 | Draft the questionnaires | bar: 2025-03-01 to 2025-05-01
13 | Second study advisory group meeting | bar: 2025-04-01
14 | Draft the analysis plan | bar: 2025-04-01 to 2025-06-01
15 | Finalise the protocol | bar: 2025-04-01 to 2025-05-01
16 | Finalise the questionnaires | bar: 2025-04-01 to 2025-05-01
17 | Submit CAG approval | bar: 2025-05-01
18 | Update the website | bar: 2025-06-01
19 | Send the protocol and questionnaires to HQIP | bar: 2025-06-01
20 | Send starter packs to local reporters (LRs) | bar: 2025-06-01
21 | Advertise the study through primary contacts (LRs) and all stakeholders | bar: 2025-06-01
22 | Advertise for reviewers through all contacts and social media | bar: 2025-06-01
23 | Create the database | bar: 2025-05-01 to 2025-07-01
24 | Start patient identification | bar: 2025-08-01
25 | Clinician questionnaires | bar: 2025-08-01 to 2026-04-01
26 | Organisational questionnaires | bar: 2025-10-01 to 2026-04-01
27 | Online patient/clinican surveys/interviews | bar: 2025-10-01 to 2026-04-01
28 | Appoint and train case reviewers | bar: 2025-09-01
29 | Reviewer meetings | bar: 2025-09-01 to 2026-03-01
30 | Data cleaning | bar: 2025-10-01 to 2025-12-01
31 | Data analysis | bar: 2026-01-01 to 2026-03-01
32 | Write the report | bar: 2026-01-01 to 2026-04-01
33 | Report production 1st review | bar: 2026-04-01 to 2026-05-01
34 | Report production 2nd review | bar: 2026-05-01 to 2026-06-01
35 | Report production 3rd review | bar: 2026-06-01 to 2026-07-01
36 | To HQIP - SRP | bar: 2026-09-01
37 | Develop QI tools | bar: 2026-10-01 to 2026-11-01
38 | PUBLISH | bar: 2026-12-01
39 | Follow-up work and stakeholder meeting 1 year on | bar: 2027-01-01 to 2027-12-01
1 | Meet with the study proposer | bar: 2025-01-01
2 | Form the study advisory group | bar: 2025-01-01 to 2025-05-01
3 | Any similar work programmes/national datasets | bar: 2025-04-01 to 2025-05-01
4 | Literature search | bar: 2025-04-01 to 2025-05-01
5 | First study advisory group meeting - key questions inc. parity of esteem and health inequalities | bar: 2025-05-01
6 | Identify methods of data collection - inclusion and exclusion | bar: 2025-05-01
7 | Set up a study web page and email | bar: 2025-06-01 to 2025-07-01
8 | Develop a communications plan - who should be involved and wider stakeholders | bar: 2025-06-01 to 2025-07-01
9 | Develop a healthcare quality improvement plan | bar: 2025-06-01 to 2025-07-01
10 | Develop a public/patient/carer involvement plan | bar: 2025-06-01 to 2025-07-01
11 | Draft the protocol | bar: 2025-06-01 to 2025-07-01
12 | Draft the questionnaires | bar: 2025-07-01 to 2025-09-01
13 | Second study advisory group meeting | bar: 2025-08-01
14 | Draft the analysis plan | bar: 2025-08-01 to 2025-10-01
15 | Finalise the protocol | bar: 2025-08-01 to 2025-09-01
16 | Finalise the questionnaires | bar: 2025-08-01 to 2025-09-01
17 | Submit CAG approval | bar: 2025-09-01
18 | Update the website | bar: 2025-10-01
19 | Send the protocol and questionnaires to HQIP | bar: 2025-10-01
20 | Send starter packs to local reporters (LRs) | bar: 2025-10-01
21 | Advertise the study through primary contacts (LRs) and all stakeholders | bar: 2025-10-01
22 | Advertise for reviewers through all contacts and social media | bar: 2025-10-01
23 | Create the database | bar: 2025-09-01 to 2025-11-01
24 | Start patient identification | bar: 2025-12-01
25 | Clinician questionnaires | bar: 2025-12-01 to 2026-08-01
26 | Organisational questionnaires | bar: 2026-02-01 to 2026-08-01
27 | Online patient/clinican surveys/interviews | bar: 2026-02-01 to 2026-08-01
28 | Appoint and train case reviewers | bar: 2026-01-01
29 | Reviewer meetings | bar: 2026-01-01 to 2026-07-01
30 | Data cleaning | bar: 2026-02-01 to 2026-04-01
31 | Data analysis | bar: 2026-05-01 to 2026-07-01
32 | Write the report | bar: 2026-05-01 to 2026-08-01
33 | Report production 1st review | bar: 2026-08-01 to 2026-09-01
34 | Report production 2nd review | bar: 2026-09-01 to 2026-10-01
35 | Report production 3rd review | bar: 2026-10-01 to 2026-11-01
36 | To HQIP - SRP | bar: 2026-12-01
37 | Develop QI tools | bar: 2027-01-01 to 2027-02-01
38 | PUBLISH | bar: 2027-03-01
39 | Follow-up work and stakeholder meeting 1 year on | bar: 2027-04-01 to 2028-03-01